TOWN OF SCITUATE   			600 Chief Justice Cushing Highway

Scituate, Massachusetts 02066

Phone:  781-545-8716

FAX:  781-545-8704

Public Building Committee

Tuesday December 15, 2015

Scituate Board of Selectmen’s Hearing Room

7:00 pm

In attendance:

Carl Campagna, Jacqueline Carr, Ed DiSalvio, David Capelle, John Lemiux, Mark Thompson, Chief John Murphy, Tricia Vinchesi, Joe Sullivan, Jessi Finnie, Shawn Harris, Nancy Holt, Joe Sullivan, Don Walters, Karen Canfield, Ashley Gonzalez, Conrad Ellos

Absent: Deputy Al Elliot, Chief Stewart, Mike Heger, Alan Brown

- Meeting Called to Order – 7:00 pm by Ed

- Agenda unanimously approved

- Meeting Minutes 10.6.15 unanimously approved 1st motion by Carl 2nd motion by Ed

PSC Update

Jon Updated the team on last week’s BOS meeting. The warrant was reopened for the additional funding; they will be article 7&8.

Ed: if article 7 passes and 8 pass, does that change the low bidder

Jon: no CTA continues to be the low bidder.

Jacqueline: once we get the funding from the town, we get bonded and insurance can something fall apart between then. Is there a way this bid can fall apart?

Jon: we have until the 20th to get the GC a contract.

Ed: all the prices you have are for the 20th

Jon: yes they are held 30 days

Ed: I have had good experience with CTA

Jon: they depend on the team; this proposed team is very experienced.

Don updated the team about the septic system; they are seeking a variance, which has become an issue. They have an option to add another tank onsite instead of going for a variance.

Ed: will it be on site?

Don: No it will still be across the street.

Jacqueline: will there be a cost

Don: yes there will be a cost for the tank

Library Update

Conrad updated the team with an overview. The asbestos abatement has been completed, the demo is still underway. During the demo they have uncovered some structural problems with the existing trusses. Tonight will be a second change order for $49,500 for mastic on the block and 3rd change order for $3,000 on the end grains. In the children’s wing during demo, the trusses showed failure. The Structural engineer came out, it appears that some of the trusses were retro fitted on site, and some are cupping on supporting membranes.  Joist hangers were only nailed 3 times where it should have been 8. They looked a repair and stabilization as well as remove and replace. The structural engineer gave costs and timelines for both.

Conrad: the asbestos is behind us and we have the change orders to approve, then we have the structural change order to look at.

Ed: the trusses lack a lot of bracing.

Joe: even on the mains there was no cross bracing to hold those up. We are building a building for the next 50 years, and we want to do it right.

Ed: what are the prices?

Conrad: full replacement for $40,000 to remove existing framing, $100,000 for a new roof.

Ed: would that be steel frame?

Conrad: that is for wood with TJI’s.

Ed: are the bearing walls in the children’s wing on foundation.

Conrad: it’s the piers only that are cantilevered.

Carl: since some trusses are hidden what is the cost of repair

Conrad: the repair approach is the time; it will take weeks for the structural engineer to analysis.

Joe: if its 3 weeks for the structural engineer there’s $13,000, $40,000 for trusses, then there is the labor which is very time consuming about $80,000, total cost of about $138,000, after all this we aren’t sure if it will make todays code with only repairs.

David: what’s the contingency that was carries?

Joe: total of $800,000

Tricia: we are $264,000 into the building without even into the contract.

Joe: $204,000 because I had $60,000 carried for abatement in the budget

Tricia: we decide to replace the whole roof, where is the expertise that is saying to replace this and it is a prudence decision?

Conrad: we can have the structural engineer put this in writing.

Tricia: that is what we need is written instruction. We need to make sure we vet these quotes; we need an itemization of the deficiencies.

Conrad: the report will be more general but the engineer knows the generals and I can have him formalize in a letter. The sooner we approve this the less money we will send. What is the process?

Tricia: if it is under $50,000 we can approve it. All BOS are aware of this issue. The BOS could vote a contingency not to exceed

Joe: if the committee motions to proceed, where can we go from there?

Tricia: The demo is not a problem it is the cost and vetting the quotes.

Ed: what does the engineer want for the redesign?

Conrad: $13,000 for repair analysis and roof replacement is $8,200

Tricia: the building commissioner walked the site, and the commissioner was very concerned with what he saw

Ed: if we go the replacement route we could vote to approve not to exceed $40,000 and get demo going, as well as approve the engineer for the $8,200

Joe: there will be a number of credits that we will qualify to get that dollar value back.

Conrad updated the team that there is also some structural issues with the main truss area. The remaining roof sections and the way it was framed are very unorthodox. The ceiling joists have to come out in order to install sprinkler and ductwork. There has been a lot of work to look at cost and time. The recommendation is to get rid of the remaining wood trusses and replace them with steel. This change would be around $100,000; this is a rough cost with hopefully some credits towards. With that change you are getting a whole new building. It seems like a 6 week delay 140 sw wing, 100 for main 40 for GC’s.

Ed: was the SW wing accessible for the structural engineer to do some due diligence.

Joe: it was in the bathroom and there was ductwork in there but I don’t think this would have uncovered the whole problem.

Tricia: I need you to come in to the BOS and lay everything out. They will ask hard questions and we need to be transparent about it.

Jacqueline: what else is out there to be lurking

Joe: it is a bare shell now after the roof is removed

Jessi: in terms of timing is it still possible to proceed with foundation before the bad weather

Conrad: we are reviewing shop drawings now, the demo of the areas are critical for the time frame.

Jessi: the $45,000 was if we were to continue demo and if we remobilize for a week; it could go up if things change

Shawn: What is the span for the trusses

Conrad: about 50’ trusses, it will be designed for current code

Shawn: has the engineer been aboard all along

Tricia: the children’s roof needs to be replaced

Jessi: since the contractor owns  removing the flooring, are there credits

Conrad: we are working with the contractor on this.

Ed: can we get a similar letter from the structural engineer to base out final decision on for the trusses and

Tricia: These are all big issues and we need to vet them with the BOS

Joe: could we approve the $8200 for the redesign

Tricia: yes

Shawn: you said more asbestos abatement, could he have been working on this until the demo is ready so he doesn’t have to mobilize

Joe: I have been doing everything in my power to keep him there.

I will get a letter from the structural engineer to approve $8200 based on public notification of the selectmen then move forward. Can this board authorize to move forward after Tuesday’s meeting.

- Motion to approve the structural engineer to complete the redesign of the Children’s wing roof, for the amount of $8,200 1st Motion Dave 2nd Karen unanimously approved.

- Motion to approve CO 2 in the amount of $49,700 for the additional asbestos removal 1st Motion Dave 2nd Jessi

- Motion to approved Requisition 2 for the amount of $383,304.10 1st motion Dave 2nd Carl

Adjournment: 9:00pm 1st motion by  Jessi, 2nd Motion by Carl

Respectfully submitted,

Lindsey DeSimone, Recording Secretary